## Sheet1
Order | Convention Tasks | Owner | Work with Whom | Date Needing to Complete | Status
1 | Hotel selected for event | District Governor |  | 1 year ahead
2 | Date selected for event | District Governor |  | 1 year ahead
3 | Negotiate contract with hotel (District Governor Signs) | District Governor |  | 1 year ahead
4 | Select Convention Theme | Convention Co-Chairs |  | ASAP
5 | Design Logo | Convention Co-Chairs |  | ASAP
6 | Meet at Hotel to review room layout and make preliminary room selection | Hotel Liaison | Convention Co-Chairs, District Governor | ASAP
7 | Select meal choices | Convention Co-Chairs | District Governor Hotel Liaison | ASAP
8 | Obtain a guaranteed room rate from the hotel, including a reservation deadline. Try to guarantee that if rates drop, our rate will drop also. | Hotel Liaison | Convention Co-Chairs, District Governor | ASAP
9 | Work with Past Chairs for info | Convention Co-Chairs |  | ASAP
10 | Recruit Committee members | Convention Co-Chairs |  | ASAP
11 | Prepare basic promotional display | Convention Co-Chairs |  | prior to District events, espec TELI and other conferences
12 | Draft the budget (determine registration prices, committee budgets, etc.) | Convention Co-Chairs | District Governor | ASAP
13 | Distribute info to Committee members - roles, responsibilities, convention info such as theme and location | Convention Co-Chairs | All Committee Chairs | Five months in advance
14 | Let chairs know what you expect from them up front | Convention Co-Chairs |  | ASAP
15 | Select your team members | All Chairs |  | ASAP
16 | Hold initial committee meeting to discuss roles and responsibilities and answer questions | Convention Co-Chairs |  | Five months in advance
17 | Work wih hotel to determine AV needs | AV Chair, Hotel Liaison | Convention Co-Chairs | Five months in advance
18 | Get proxy info out to all clubs asap | LGET |  | Four months in advance
19 | Review and approve budget | District Governor |  | 3 months in advance
20 | Prepare Registration form | Convention Co-Chairs |  | 3 months in advance
21 | Create online Registration | Cliff Heinsch |  | 3 months in advance
22 | Start preparing script and times. Consider both a spreadhseet format and a word format. | Convention Co-Chairs | District Governor, LGET, SAA | 3 months in advance
23 | List of equipment needs for the weekend. | Convention Co-Chairs | SAA, AV Chair | 7-8 weeks in advance
24 | Set PDG and 25-year club meeting times and locations, inform PDG group and 25 year club. | Convention Co-Chairs | District Governor | 7-8 weeks in advance
25 | Contact 25 year club | Convention Co-Chairs |  | 7-8 weeks in advance
26 | Contact PDG group | Convention Co-Chairs |  | 7-8 weeks in advance
27 | Determine what signage exists that can be re-used | Convention Co-Chairs | SAA | 7-8 weeks in advance
28 | Update Promotional Display with additional information | Convention Co-Chairs |  | 7-8 weeks in advance
29 | Distribute info to Committee members - roles, responsibilities, convention info such as theme and location, budget, etc | Convention Co-Chairs | All Committee Chairs | 7-8 weeks in advance
30 | Promotion information on Website | Convention Co-Chairs |  | 7-8 weeks in advance
31 | Finalize Overall Event Schedule to post on web and get in Digest | Convention Co-Chairs |  | 7-8 weeks in advance
32 | On Line Registration is available | Convention Co-Chairs |  | 7-8 weeks in advance
33 | PDF registration form available on website | Convention Co-Chairs | PRO, Registration | 7-8 weeks in advance
34 | Promote info to Division Governors to send to AGs and to Clubs. Be sure to include registration deadline | Convention Co-Chairs |  | 7-8 weeks in advance
35 | Put Preliminary Schedule on website | Convention Co-Chairs | Public Relations Officer | ASAP after Teli
36 | Contact photographers | Convention Co-Chairs |  | 7-8 weeks in advance
37 | Photographers - if there are any specific photos needed, notify photographers | District Governor | Convention Co-Chairs | 7-8 weeks in advance
38 | Promote Convention at each Division Contest-determine who can attend what contest | Convention Co-Chairs |  | 7-8 weeks in advance
39 | Follow up with all committee chairs on progress | Convention Co-Chairs |  | 7-8 weeks in advance
40 | Verify meal choices with hotel | Convention Co-Chairs |  | 7-8 weeks in advance
41 | Re-check with hotel on room rate; check online rates for any differences | Convention Co-Chairs |  | 7-8 weeks in advance
42 | Hold subsequent committee meeting to check in on progress | Convention Co-Chairs |  | 7-8 weeks in advance
43 | Draft Script | District Governor | Convention Co-Chairs, LGET, SAA | 7-8 weeks in advance
44 | Contact PDG group for display of past Dsitrrict Governor photos (Judy S/Cliff H) | District Governor |  | 7-8 weeks in advance
45 | Determine and buy decorations for the conference/convention | Decorations Chair |  | 7-8 weeks in advance
46 | Contact Mayor or city offical for Saturday breakfast | District Governor |  | 7-8 weeks in advance
47 | Create eval form for educational session (if new one is needed) | Education Chair |  | 7-8 weeks in advance
48 | Selects and books entertainment | Friday Fun Night Chair | District Governor, Convention Co-Chairs | 7-8 weeks in advance
49 | Obtain info about host city; possibly obtain freebies to distribute (eg to first-timers; speakers, etc) | Hospitality Chair |  | 7-8 weeks in advance
50 | Boy Scouts and color guard organized for Saturday breakfast | Hospitality Chair |  | 7-8 weeks in advance
51 | Draft Script # 2 | LGET | Convention Co-Chairs, District Governor, SAA | 7-8 weeks in advance
52 | Select menu for leadership Breakfast Sunday morning | LGET |  | 7-8 weeks in advance
53 | Begin Design for the programs | Program Chair |  | 7-8 weeks in advance
54 | #10 Envelope for Cash and Checks while holding them | Registration Chair |  | 7-8 weeks in advance
55 | Create Alpha File for receipts | Registration Chair |  | 7-8 weeks in advance
56 | Order Extra Ribbons as needed | Registration Chair |  | 7-8 weeks in advance
57 | Canvas local businesses, other TM for Donations | Silent Auction Chair | Division Governors, local businesses | 7-8 weeks in advance
58 | Announcement on website requesting silent auction donations. Consider any other PR outlets such as District Digest. | Silent Auction Chair | Public Relations Officer | 7-8 weeks in advance
59 | Think about possible unexpected events…. And plan ahead for them - e.g. Speaker backs out; power goes out, bad weather | Convention Co-Chairs |  | 7-8 weeks in advance
60 | Spring - Will there be PR contest recognition at Sat breakfast? Do they need reserved tables | Convention Co-Chairs | Public Relations Officer | 7-8 weeks in advance
61 | Order and engrave trophies for contests | District Governor |  | 7-8 weeks in advance
62 | Prepare article for District 6 Digest to promote the convention. Get to District Governor and Digest Editor | Convention Co-Chairs |  | 5-6 weeks in advance
63 | Plan First Timer Program | First Timer Chair |  | 5-6 weeks in advance
64 | Recruits greeters and information table (if there is one). | Hospitality Chair |  | 5-6 weeks in advance
65 | Recruit people to serve as helpers as needed for Friday Fun Night activities/food | Hospitality Chair |  | 5-6 weeks in advance
66 | Recruit people to serve as helpers for Saturday hospitality if needed | Hospitality Chair |  | 5-6 weeks in advance
67 | Recruit helpers to take tickets at buffet-style meals if needed | Hospitality Chair |  | 5-6 weeks in advance
68 | Recruit volunteers to help staff Registration Table | Registration Chair | Hospitality Chair | 5-6 weeks in advance
69 | Recruit volunteers to help staff Rsource Center | Resource Center Chair | Hospitality Chair | 5-6 weeks in advance
70 | Recruit and schedule volunteeers for Silent auction | Silent Auction Chair | Hospitality Chair | 5-6 weeks in advance
71 | Obtain assistants to help set up decorations | Decorations Chair | Hospitality Chair | 5-6 weeks in advance
72 | Coordinate all facilities requirements | Hotel Liaison |  | 5-6 weeks in advance
73 | Programs - request intro info from Trio for general program | Program Chair | District Governor, LGET, LGM | 5-6 weeks in advance
74 | Design programs review #1 | Program Chair | Committees | 5-6 weeks in advance
75 | Obtain map of hotel for general program | Program Chair | Hotel Liaison | 5-6 weeks in advance
76 | Set up Facebook info, Linked in, anything else to publicize. | Public Relations Officer |  | 5-6 weeks in advance
77 | Visit Division contests and promote | Convention Co-Chairs |  | 5-6 weeks in advance
78 | Follow up with all committee chairs on progress | Convention Co-Chairs |  | 4 weeks in advance
79 | For evaluation contest, select a target speaker | District Governor |  | 4 weeks in advance
80 | Give club information to Credentials Chair | District Governor |  | 4 weeks in advance
81 | Remind Committee and Division Governors to book hotel rooms by stated due date to get TM rate | Convention Co-Chairs |  | 4 weeks in advance
82 | Hold subsequent committee meeting to check in on progress | Convention Co-Chairs |  | 4 weeks in advance
83 | ID Don Murray award winner | District Governor |  | 4 weeks in advance
84 | ID Lorin Pollmann award winner | District Governor |  | 4 weeks in advance
85 | ID Lou Novak award winner | District Governor |  | 4 weeks in advance
86 | Coordinate International Director Visit, if applicable | District Governor |  | 4 weeks in advance
87 | Selects Toastmaster for Friday night | District Governor |  | 4 weeks in advance
88 | Write and send invitation letter to 25 year clubs | District Governor |  | 4 weeks in advance
89 | Select presenters for Ed sessions | LGET |  | 4 weeks in advance
90 | Assign Session Conveners, typically Division Governors | LGET |  | 4 weeks in advance
91 | Obtain keynote speaker for event , if needed | LGET |  | 4 weeks in advance
92 | Copy Evaluation Forms for the Educational Sessions | LGET |  | 4 weeks in advance
93 | prepare packets of information for First Timers | First Timer Chair |  | 4 weeks in advance
94 | Prepare Welcome Speech for Friday Night | Hospitality Chair |  | 4 weeks in advance
95 | Review guaranteed room rate with the hotel. Ensure there are no other better deals (e.g.online). Update registration info if necessary. | Hotel Liaison |  | 4 weeks in advance
96 | Order food for leadership breakfast Sunday morning | LGET | Hotel Liaison | 4 weeks in advance
97 | If evaluation contest, get legal pads and pend for the evaluation contestants | LGET |  | 4 weeks in advance
98 | Act as Toastmaster for Spring Saturday Contest | LGET |  | 4 weeks in advance
99 | Act as Toastmaster for Fall Saturday Contest | LGM |  | 4 weeks in advance
100 | Write thank you notes to all convention helpers | Convention Co-Chairs |  | 4 weeks in advance
101 | Website/PR update as needed | Public Relations Officer |  | 4 weeks in advance
102 | Have Signs for Table: Pre-Paid; To Pay | Registration Chair |  | 4 weeks in advance
103 | Large Envelope or Basket for Drawing at the Banquet (Secretary) | Registration Chair |  | 4 weeks in advance
104 | Obtain supplies for registration desk | Registration Chair |  | 4 weeks in advance
105 | Copy Convention Evaluation Forms to insert into Registration packets | Registration Chair |  | 4 weeks in advance
106 | Boxes to pick up ballots after business meeting | SAA |  | 4 weeks in advance
107 | Create "reserved" signs for the Divisions for contestants | Convention Co-Chairs |  | 4 weeks in advance
108 | Obtain Trophies for contests | District Governor |  | 4 weeks in advance
109 | Purchase District award plaques/Get engraved | District Governor | LGET | 4 weeks in advance
110 | Draft Script # 3 | Convention Co-Chairs | District Governor, SAA | 4 weeks in advance
111 | Discuss details for contest with District Governor | Contest Toastmaster |  | 3 weeks in advance
112 | Review Speech Contest Guide http://docs.d6tm.org/Hosting_a_Successful_Club_Contest.doc for full list of contest duties. | Contest Toastmaster, Chief judge |  | 3 weeks in advance
113 | Review script with entire convetnion committee | Convention Co-Chairs |  | 3 weeks in advance
114 | Confirm with Registration Chair - requirements for Registration setup and reporting through the event | Convention Co-Chairs | Registration Chair | 3 weeks in advance
115 | Credentials desk schedule and set up | Credentials Chair |  | 3 weeks in advance
116 | Prepare Credentials books and ballots | Credentials Chair |  | 3 weeks in advance
117 | Arrange for club members to carry banners for DG, LGET, LGM | District Governor |  | 3 weeks in advance
118 | Arrange for Invocators for meals , business meetings, and toastmaster for Friday contest; persons to lead the Canadian and US pledges, the toasts to the US President and Prime Minister of Canada | District Governor |  | 3 weeks in advance
119 | Confirm with invocators etc to arrive 15 minutes or so AHEAD of the time scheduled in the script, to allow for the possibility of running ahead of schedule. | District Governor |  | 3 weeks in advance
120 | Select person to sing national anthem at Saturday Dinner | District Governor |  | 3 weeks in advance
121 | Remind Division Governors to be ready with 1-2 minute report for business meeting | District Governor |  | 3 weeks in advance
122 | Remind Division Governors to bring pins for Sat night | District Governor |  | 3 weeks in advance
123 | Representatives in place from District Governor and LGET’s home clubs for DG banner transfer | District Governor | LGET | 3 weeks in advance
124 | Get International Director information if ID is visiting | District Governor | LGET | 3 weeks in advance
125 | For Evaluation contest - Coordinate with Target Speaker - have them arrive early if they want to have a microphone check, so as not to interfere with contestant meeting. | District Governor |  | 3 weeks in advance
126 | Get bios and speech info from Ed presenters | LGET |  | 3 weeks in advance
127 | Prepare presenter packets for educational sessions | LGET | SAA | 3 weeks in advance
128 | Put in request for room arrangements and equipment needed- | Hotel Liaison |  | 3 weeks in advance
129 | Advise LGET of presentation needs (overhead projector, flip charts, etc.) | Educational Presenters |  | 3 weeks in advance
130 | Ensure presenters know they must register for at least the Events section of the convention. | LGET |  | 3 weeks in advance
131 | Order beverages for 25 year and PDG meetings | Hotel Liaison |  | 3 weeks in advance
132 | Provide a written introduction to LGET | Educational Presenters |  | 3 weeks in advance
133 | Write an intro for the Friday Fun Night activities | Friday Fun Night Chair |  | 3 weeks in advance
134 | Coordinate with Hotel to determine when hotel bill will be ready for review. | Hotel Liaison | Convention Co-Chairs | 3 weeks in advance
135 | Check with Treasurer for process to get hotel bill paid, depending on when it will be received. | Convention Co-Chairs | Hotel Liaison | 3 weeks in advance
136 | Provide bio and photo (if requested) as soon as you have your commitment – to be in program and advertising | Keynote Speaker |  | 3 weeks in advance
137 | Discuss details for contest with District Governor | LGET |  | 3 weeks in advance
138 | Review Speech Contest Guide http://docs.d6tm.org/Hosting_a_Successful_Club_Contest.doc for full list of contest duties. | LGET |  | 3 weeks in advance
139 | Discuss details for contest with District Governor | LGM |  | 3 weeks in advance
140 | Review Speech Contest Guide http://docs.d6tm.org/Hosting_a_Successful_Club_Contest.doc for full list of contest duties. | LGM |  | 3 weeks in advance
141 | Confirm Inspirations and other names for programs | Program Chair | District Governor | 3 weeks in advance
142 | Design programs review #2 | Program Chair | Committees | 3 weeks in advance
143 | Coordinate all equipment needs for educational sessions, special events and contests | SAA |  | 3 weeks in advance
144 | Signage design update | Signage Chair |  | 3 weeks in advance
145 | Determine number of tables needed | Silent Auction Chair |  | 3 weeks in advance
146 | Set up Sllent Auction schedule | Silent Auction Chair |  | 3 weeks in advance
147 | Check registration counts | Convention Co-Chairs | Registration Chair | 2 weeks in advance
148 | Confirm program design and information | Convention Co-Chairs | Program Chair | 2 weeks in advance
149 | Hold final committee meeting at Hotel | Convention Co-Chairs |  | 2 weeks in advance
150 | Arrange for promo of the next conference/ convention at the Saturday night dinner | Convention Co-Chairs |  | 2 weeks in advance
151 | Arrange for tables in main rooms for Trophies, timing, and any other decorations | Convention Co-Chairs |  | 2 weeks in advance
152 | Follow up with all committee chairs on progress | Convention Co-Chairs |  | 2 weeks in advance
153 | Prepare Opening remarks for Friday Evening - welcome to everyone, have fun | Convention Co-Chairs |  | 2 weeks in advance
154 | Use list of registered attendees and followup with those not yet registered; Contestants, Educational presenters, Division Governors | Convention Co-Chairs | LGET | Two weeks ahead
155 | Compute the beginning of the list of digntaries for recognition, marchin and head table setup. | Convention Co-Chairs |  | Two weeks ahead
156 | Work with District Governor on seating for head table | Convention Co-Chairs |  | 2 weeks in advance
157 | Create business meeting agenda | District Governor |  | 2 weeks in advance
158 | Get gift for International Director if needed | District Governor |  | 2 weeks in advance
159 | Provide certificates for contests | District Governor |  | 2 weeks in advance
160 | Friday Fun Night details completed | Friday Fun Night Chair |  | 2 weeks in advance
161 | Historian collects names of those who have passed and reports at C&L lunch | Historian |  | 2 weeks in advance
162 | Get greeters confirmed and schedule completed | Hospitality Chair |  | 2 weeks in advance
163 | Work with hotel on seating arrangements | Hotel Liaison |  | 2 weeks in advance
164 | Coordinate with hotel to make sure front table is always served first. | Hotel Liaison |  | 2 weeks in advance
165 | Determine spouses/guests of people at head table for table layout and name tents | Hotel Liaison |  | 2 weeks in advance
166 | Coordinate number of tables with Hotel | Hotel Liaison | SAA | 2 weeks in advance
167 | Order food and beverage for Sun AM leadership meeting | LGET |  | 2 weeks in advance
168 | Advise Toastmaster and program Chair of names of contestants | LGET |  | 2 weeks in advance
169 | Verify eligibility of contestants | LGET |  | 2 weeks in advance
170 | Confirm contestant names | Program Chair |  | 2 weeks in advance
171 | Design programs review #3 | Program Chair | Committees | 2 weeks in advance
172 | Copy extra Registration Forms for Same-Day Registrations | Registration Chair |  | 2 weeks in advance
173 | Start to create Registration Packets: for all attendees; name badge; meal tickets; overall conf eval, ribbons | Registration Chair |  | 2 weeks in advance
174 | Extra Meal Tickets | Registration Chair |  | 2 weeks in advance
175 | Provide list of all attendees to Co-chairs. | Registration Chair | Convention Co-Chairs | Two weeks ahead
176 | Bring timing lights; timing devices for all sessions | SAA |  | 2 weeks in advance
177 | Collect Silent Auction Donations | Silent Auction Chair |  | 2 weeks in advance
178 | Prepare Bid sheets for all auction items | Silent Auction Chair |  | 2 weeks in advance
179 | Update Silent Auction Donor list | Silent Auction Chair |  | 2 weeks in advance
180 | Confirm # of Breakfast Tickets for the Color Guard | Hospitality Chair | Registration Chair | 1 week in advance
181 | Final script review | Convention Co-Chairs | District Governor | 2 weeks in advance
182 | check registration counts | Convention Co-Chairs | Registration Chair | 1 week in advance
183 | Get updated list of Registered attendees | Convention Co-Chairs | Registration Chair | 1 week in advance
184 | Continue to create Registration Packets: for all attendees; name badge; meal tickets; overall conf eval, ribbons | Registration Chair
185 | Coordinate seating for head table. Follow up on non-registrants, if applicable | Convention Co-Chairs | SAA | 1 week in advance
186 | final counts of tables for displays | Convention Co-Chairs | Auction Chair, Merchandise Chair, others | 1 week in advance
187 | review any special accommodations | Convention Co-Chairs |  | 1 week in advance
188 | Confirm # of meals with Hotel | Convention Co-Chairs |  | 1 week in advance
189 | Figure out quantity of extra chairs for contest-only seating for both contests | Convention Co-Chairs |  | 1 week in advance
190 | Proof to make sure times are correct on ALL materials (programs/flyers/web site, etc) | Convention Co-Chairs |  | 1 week in advance
191 | Hotel will provide you with Event Orders, listing what is shceudled when, including the guarantee for number of meals. Review to ensure accuracy and make needed changes. | Convention Co-Chairs |  | Week before
192 | Determine seating for head table – all meals where it is warranted. | District Governor |  | 1 week in advance
193 | Provide all handouts for District meeting | District Governor |  | 1 week in advance
194 | Pirnt copies of script for Co-Chairs and SAA | District Governor |  | 1 week in advance
195 | Makes sure their team has the information needed for this convention/conference | Hospitality Chair |  | 1 week in advance
196 | Head table counts to Hotel | Hotel Liaison |  | 1 week in advance
197 | Design programs final review | Program Chair and everyone | Committees | 1 week in advance
198 | Finalize programs | Program Chair | Convention Co-Chair | 1 week in advance
199 | Prints final programs | Program Chair |  | 1 week in advance
200 | Create name badges for all guests with appropriate meal tickets (e.g. ID, Speakers | Registration Chair |  | 1 week in advance
201 | Create Registration Packets: for all attendees; name badge; meal tickets; overall conf eval, ribbons | Registration Chair |  | 1 week in advance
202 | Provide list of allattendees / dignitaries attending to SAA and Co-chairs for acknowledgements and march-in | Registration Chair |  | 1 week in advance
203 | Provide meal counts to Co-chairs/hotel | Registration Chair |  | 1 week in advance
204 | Prepare Thank you letters to all donors | Silent Auction Chair |  | 1 week in advance
205 | Pick up last minute donations | Silent Auction Chair |  | 1 week in advance
206 | Prepare Name tents for every possible person at head tables - check name spelling - print tents on both sides. | Who? |  | 1 week in advance
207 | Create list of donors (silent auction and all others) | Silent Auction Chair | Convention Co-Chairs | 2 days before
208 | Compute list of digntaries for recognition, marchin and head table setup. | Convention Co-Chairs |  | Day before the event
209 | Provide list of all attendees to Co-chairs. | Registration Chair | Convention Co-Chairs | Day before the event
210 | Confirm greeters know what to do and are in position at proper times | Hospitality Chair |  | Day of event
211 | Deposit checks/cash with District Treasurer as received | Registration Chair |  | all along
212 | Set up Resource Center | Resource Center Chair |  | Day of event
213 | Make sure signage is in appropriate locations | SAA |  | Day of event
214 | Start all of the meetings/introductions | SAA |  | Day of event
215 | Set programs on tables at each event | SAA / Decorations chair? |  | Day of event
216 | Set up Slient Auction | Silent Auction Chair |  | Day of event
217 | Run the auction | Silent Auction Chair |  | Day of event
218 | Run the Resource Center | Resource Center Chair |  | Day of event
219 | Serve as contest Sergeant-At-Arms | SAA |  | Day of event
220 | Set up decorations for the conference/convention | Decorations Chair |  | Friday
221 | Verify attendees and that we have name tents and spots at the head tables for everyone. Have blanks available if needed. | Convention Co-Chairs |  | Friday
222 | Have box at registration table for convention evaluations | Registration Chair |  | Friday
223 | Have change available for walk-ins | Registration Chair |  | Friday
224 | Have sign for a Box: Conference Evaluations | Registration Chair |  | Friday
225 | Provide last minute walk-ins of any dignitaries attending to SAA and Co-chairs for acknowledgements and march-in | Registration Chair |  | Friday
226 | Same-Day Name Tags – either peel-off or make hanging badges | Registration Chair |  | Friday
227 | Invite First Timers to sit with someone | First Timer Chair |  | Friday
228 | Watches over refreshments and refills/reorders as needed | Hospitality Chair |  | Friday
229 | Return all contest paperwork to the District Governor immediately following the meeting. | Contest Toastmaster |  | Friday
230 | Monitor Everything!! | Convention Co-Chairs |  | Friday
231 | Hands out materials to session conveners | Registration Chair |  | Saturday
232 | Set up decorations for the conference/convention | Decorations Chair |  | Saturday
233 | Facilitate the parade of banners Saturday morning | SAA |  | Saturday
234 | Meet the mayor and escort to breakfast | LGM |  | Saturday
235 | Return all contest paperwork to the District Governor immediately following the meeting. | LGET |  | Saturday
236 | Return all contest paperwork to the District Governor immediately following the meeting. | LGM |  | Saturday
237 | Monitor Everything!! | Convention Co-Chairs |  | Saturday
238 | Submit final reimbursement requests to Treasurer | All Chairs | Treasurer | Week after the event
239 | Followup with key chairs/District Officers on how things went/lessons learned/ possible | Convention Co-Chairs | All Committee Chairs | By three weeks after the event
240 | Prepare convention summary blurb for website posting | Convention Co-Chairs | Webmaster | Immediately after the event
241 | Receive Hotel Bill; verify for correctness, route to District officers | Convention Co-Chairs |  | Week after the event
242 | Obtain information from all Chairs on expenses and compute final actual income/expenses report | Convention Co-Chairs | Treasurer | By three weeks after the event
243 | Report final numbers of attendees/paid for each event | Registration Chair | Convention Co-Chairs | Week after the event
244 | Remove Convention information from district website and and replace with blurb summarizing how it went | Webmaster |  | Immediately after the event